## UAT Report
-- COPY THIS AREA IN THE ACK EMAIL BODY --
Aplikasi Booking Room Hotel
- Project Information - |  | - Test Result - |  |  |  | - Execution Plan - |  | - Actual Execution -
Report Date. | 2021-09-13 | Status. |  |  |  | Start Date. | 2021-09-10 | Start Date. | 2021-09-10
Project No. |  | Completion. |  |  |  | Finish Date. | 2021-09-15 | Finish Date. | 2021-09-15
Test Cycle. |  | Total Test Case. | 88
Test Env. | Development
- Total Results To Date -
Status. | Planned #. | Planned % | Actual #. | Actual % from Result to Date.
Plan. | 88 | 100%
Tested correctly | 88 | 100% | 85 | 96.59%
Tested with non Stopping Defect |  |  | 2 | 2.273%
Tested with Showstopper |  |  | 1 | 1.136%
In Progress |  |  | 0 | 0%
N/A |  |  | 0 | 0%
Not Tested |  |  | 0 | 0%
- Defect / Issue Details -
Defect ID (#) | Defect Name | Description |  | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case
No. | Type. | Scenario ID | Scenario Case |  |  |  |  | Result. | Blocked by (Defect ID)
1 | Positive | Room001 | User create Account Aplikasi Booking Room Hotel |  |  |  |  | Tested correctly
2 | Positive | Room002 | User Create Account with Email Registered |  |  |  |  | Tested correctly
3 | Positive | Room003 | User Register Account but FirstName is Numeric |  |  |  |  | Tested correctly
4 | Positive | Room004 | User Register Account but LastName is Numeric |  |  |  |  | Tested correctly
5 | Positive | Room005 | User Register Account but FirstName is Special Character |  |  |  |  | Tested correctly
6 | Positive | Room006 | User Register Account but LastName is Special Character |  |  |  |  | Tested correctly
7 | Positive | Room007 | User Register Account but Password is less than 5 Chars |  |  |  |  | Tested correctly
8 | Positive | Room008 | User Register Account but FirstName only 1 Character |  |  |  |  | Tested correctly
9 | Positive | Room009 | User Register Account but LarstName only 1 Character |  |  |  |  | Tested correctly
10 | Positive | Room010 | User update the Address but phone number is Empty |  |  |  |  | Tested correctly |  | -- COPY THIS AREA IN THE ACK EMAIL BODY --
11 | Positive | Room011 | User login Aplikasi Booking Room Hotel |  |  |  |  | Tested correctly
12 | Positive | Room012 | User login Aplikasi Booking Room Hotel but invalid email format |  |  |  |  | Tested correctly
13 | Positive | Room013 | User forgot the password |  |  |  |  | Tested with Showstopper
14 | Positive | Room014 | User Add a New the Address |  |  |  |  | Tested correctly
15 | Positive | Room015 | User Add a New the Address but address1 is empty |  |  |  |  | Tested correctly
16 | Positive | Room016 | User Add a New the Address but city is empty |  |  |  |  | Tested correctly
17 | Positive | Room017 | User Add a New the Address but phone is empty |  |  |  |  | Tested correctly
18 | Positive | Room018 | User Add a New the Address but country is empty |  |  |  |  | Tested correctly
19 | Positive | Room019 | User Add a New the Address but the Zip/Postal is empty |  |  |  |  | Tested correctly
20 | Positive | Room020 | User Update the Address |  |  |  |  | Tested correctly
21 | Positive | Room021 | User update the Address but firstname is Empty |  |  |  |  | Tested correctly
22 | Positive | Room022 | User update the Address but lastname is Empty |  |  |  |  | Tested correctly
23 | Positive | Room023 | User update the Address but address1 is Empty |  |  |  |  | Tested correctly
24 | Positive | Room024 | User update the Address but city is Empty |  |  |  |  | Tested correctly
25 | Positive | Room025 | User update the Address but phone number is Empty |  |  |  |  | Tested correctly
26 | Positive | Room026 | User update the Address but the zip/postal code is Empty |  |  |  |  | Tested correctly
27 | Positive | Room027 | User update the Address but the Adress title is Empty |  |  |  |  | Tested correctly
28 | Positive | Room028 | User Delete the Address |  |  |  |  | Tested correctly
29 | Positive | Room029 | User see the Address |  |  |  |  | Tested correctly
30 | Positive | Room030 | User see Personal Information |  |  |  |  | Tested correctly
31 | Positive | Room031 | User see Order history and details |  |  |  |  | Tested correctly
32 | Positive | Room032 | User see My Credit Slips |  |  |  |  | Tested correctly
33 | Positive | Room033 | User searching Hotel but date Check In less than today |  |  |  |  | Tested correctly
34 | Positive | Room034 | User searching Hotel but Hotel Location Empty |  |  |  |  | Tested correctly
35 | Positive | Room035 | User searching Hotel but room not selected |  |  |  |  | Tested correctly
36 | Positive | Room036 | User searching Hotel but not fields selected |  |  |  |  | Tested correctly
37 | Positive | Room037 | User searching Hotel but only set Hotel Location |  |  |  |  | Tested correctly
38 | Positive | Room038 | User searching Hotel but only set the Hotel |  |  |  |  | Tested correctly
39 | Positive | Room039 | User searching Hotel but only set Check In Date |  |  |  |  | Tested correctly
40 | Positive | Room040 | User searching Hotel but only set Check Out Date |  |  |  |  | Tested correctly
41 | Positive | Room041 | User searching Hotel but date Check In and Check Out is today |  |  |  |  | Tested correctly
42 | Positive | Room042 | User validate cart |  |  |  |  | Tested correctly
43 | Positive | Room043 | User see Profile Account |  |  |  |  | Tested correctly
44 | Positive | Room044 | User see Burger Menu |  |  |  |  | Tested correctly
45 | Positive | Room045 | User see Interior section |  |  |  |  | Tested correctly
46 | Positive | Room046 | User see Amenities section |  |  |  |  | Tested correctly
47 | Positive | Room047 | User see Our Room section |  |  |  |  | Tested correctly
48 | Positive | Room048 | User Booking Deluxe Rooms in Our Room section |  |  |  |  | Tested correctly
49 | Positive | Room049 | User Booking Executive Rooms in Our Room section |  |  |  |  | Tested correctly
50 | Positive | Room050 | User Booking General Rooms in Our Room section |  |  |  |  | Tested correctly
51 | Positive | Room051 | User Booking Luxury Rooms in Our Room section |  |  |  |  | Tested correctly
52 | Positive | Room052 | User modify search in Detail Room Page |  |  |  |  | Tested correctly
53 | Positive | Room053 | User view photos in Detail Room Page |  |  |  |  | Tested correctly
54 | Positive | Room054 | User write a review in Detail Room Page |  |  |  |  | Tested correctly
55 | Positive | Room055 | User see Room Information in Detail Room Page |  |  |  |  | Tested correctly
56 | Positive | Room056 | User see Refund Policies in Detail Room Page |  |  |  |  | Tested correctly
57 | Positive | Room057 | User see Reviews in Detail Room Page |  |  |  |  | Tested correctly
58 | Positive | Room058 | User see Testimony Guest in testimoni section |  |  |  |  | Tested correctly
59 | Positive | Room059 | User change language in footer section |  |  |  |  | Tested correctly
60 | Positive | Room060 | User see about information in footer section |  |  |  |  | Tested correctly
61 | Positive | Room061 | User Subscribe to Get Notifications in footer section |  |  |  |  | Tested correctly
62 | Positive | Room062 | User follows Social Media in footer section |  |  |  |  | Tested correctly
63 | Positive | Room063 | User see Explore Information in footer section |  |  |  |  | Tested correctly
64 | Positive | Room064 | User searching room based on Rating Ascending |  |  |  |  | Tested with non Stopping Defect
65 | Positive | Room065 | User searching room based on Rating Descending |  |  |  |  | Tested with non Stopping Defect
66 | Positive | Room066 | User searching room based on Price Highest Price |  |  |  |  | Tested correctly
67 | Positive | Room067 | User searching room based on Price Lowest Price |  |  |  |  | Tested correctly
68 | Positive | Room068 | User searching room based on Guest Rating |  |  |  |  | Tested correctly
69 | Positive | Room069 | User searching room based on Amenities |  |  |  |  | Tested correctly
70 | Positive | Room070 | User searching Room in Category Room page |  |  |  |  | Tested correctly
71 | Positive | Room071 | User see Order Detail Page |  |  |  |  | Tested correctly
72 | Positive | Room072 | User confirm the order use Bank Wire as Payment Method |  |  |  |  | Tested correctly
73 | Positive | Room073 | User confirm the order use check as Payment Method |  |  |  |  | Tested correctly
74 | Positive | Room074 | User Checkout Room from cart Item |  |  |  |  | Tested correctly
75 | Positive | Room075 | User delete Cart Item |  |  |  |  | Tested correctly
76 | Positive | Room076 | User confirm the order use Pay Pal as Payment Method |  |  |  |  | Tested correctly
77 | Positive | Room077 | User see Order Confirmation |  |  |  |  | Tested correctly
78 | Positive | Room078 | User see Order history and details |  |  |  |  | Tested correctly
79 | Positive | Room079 | User Checkout order Room Hotel as a Guest |  |  |  |  | Tested correctly
80 | Positive | Room080 | User register Guest Information but Firstname is empty |  |  |  |  | Tested correctly
81 | Positive | Room081 | User register Guest Information but Lastname is empty |  |  |  |  | Tested correctly
82 | Positive | Room082 | User register Guest Information but Email is empty |  |  |  |  | Tested correctly
83 | Positive | Room083 | User register Guest Information but Password is empty |  |  |  |  | Tested correctly
84 | Positive | Room084 | User register Guest Information but Mobile is empty |  |  |  |  | Tested correctly
85 | Positive | Room085 | User register Guest Information but Email is Registered |  |  |  |  | Tested correctly
86 | Positive | Room086 | User register Guest Information but Password less than 5 characters |  |  |  |  | Tested correctly
87 | Positive | Room087 | User sending message via Contact Us |  |  |  |  | Tested correctly
88 | Positive | Room088 | User Logout Aplikasi Booking Room Hotel |  |  |  |  | Tested correctly

## UAT Scenario
No | Scenario ID | Scenario Cases | Feature | Involved System or Application | Scenario Type | Planned Date | Execution Date | Status | Tester | Notes
1 | Room001 | User create Account Aplikasi Booking Room Hotel | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
2 | Room002 | User Create Account with Email Registered | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
3 | Room003 | User Register Account but FirstName is Numeric | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
4 | Room004 | User Register Account but LastName is Numeric | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
5 | Room005 | User Register Account but FirstName is Special Character | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
6 | Room006 | User Register Account but LastName is Special Character | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
7 | Room007 | User Register Account but Password is less than 5 Chars | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
8 | Room008 | User Register Account but FirstName only 1 Character | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
9 | Room009 | User Register Account but LarstName only 1 Character | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
10 | Room010 | Scenario ID | Register Account | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
11 | Room011 | User login Aplikasi Booking Room Hotel | Login | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
12 | Room012 | User login Aplikasi Booking Room Hotel but invalid email format | Login | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
13 | Room013 | User forgot the password | Forgot Password | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
14 | Room014 | User Add a New the Address | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
15 | Room015 | User Add a New the Address but address1 is empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
16 | Room016 | User Add a New the Address but city is empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
17 | Room017 | User Add a New the Address but phone is empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
18 | Room018 | User Add a New the Address but country is empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
19 | Room019 | User Add a New the Address but the Zip/Postal is empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
20 | Room020 | User Update the Address | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
21 | Room021 | User update the Address but firstname is Empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
22 | Room022 | User update the Address but lastname is Empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
23 | Room023 | User update the Address but address1 is Empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
24 | Room024 | User update the Address but city is Empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
25 | Room025 | User update the Address but phone number is Empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
26 | Room026 | User update the Address but the zip/postal code is Empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
27 | Room027 | User update the Address but the Adress title is Empty | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
28 | Room028 | User Delete the Address | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
29 | Room029 | User see the Address | Address | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
30 | Room030 | User see Personal Information | Personal Information | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
31 | Room031 | User see Order history and details | Order History | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
32 | Room032 | User see My Credit Slips | Credit Slips | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
33 | Room033 | User searching Hotel but date Check In less than today | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
34 | Room034 | User searching Hotel but Hotel Location Empty | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
35 | Room035 | User searching Hotel but room not selected | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
36 | Room036 | User searching Hotel but not fields selected | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
37 | Room037 | User searching Hotel but only set Hotel Location | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
38 | Room038 | User searching Hotel but only set the Hotel | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
39 | Room039 | User searching Hotel but only set Check In Date | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
40 | Room040 | User searching Hotel but only set Check Out Date | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
41 | Room041 | User searching Hotel but date Check In and Check Out is today | Search Room | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
42 | Room042 | User validate cart | Homepage | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
43 | Room043 | User see Profile Account | Homepage | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
44 | Room044 | User see Burger Menu | Homepage | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
45 | Room045 | User see Interior section | Homepage | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
46 | Room046 | User see Amenities section | Homepage | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
47 | Room047 | User see Our Room section | Booking Now | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
48 | Room048 | User Booking Deluxe Rooms in Our Room section | Booking Now | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
49 | Room049 | User Booking Executive Rooms in Our Room section | Booking Now | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
50 | Room050 | User Booking General Rooms in Our Room section | Booking Now | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
51 | Room051 | User Booking Luxury Rooms in Our Room section | Room Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
52 | Room052 | User modify search in Detail Room Page | Room Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
53 | Room053 | User view photos in Detail Room Page | Room Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
54 | Room054 | User write a review in Detail Room Page | Room Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
55 | Room055 | User see Room Information in Detail Room Page | Room Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
56 | Room056 | User see Refund Policies in Detail Room Page | Room Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
57 | Room057 | User see Reviews in Detail Room Page | Room Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
58 | Room058 | User see Testimony Guest in testimoni section | Footer | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
59 | Room059 | User change language in footer section | Footer | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
60 | Room060 | User see about information in footer section | Footer | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
61 | Room061 | User Subscribe to Get Notifications in footer section | Footer | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
62 | Room062 | User follows Social Media in footer section | Footer | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
63 | Room063 | User see Explore Information in footer section | Footer | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
64 | Room064 | User searching room based on Rating Ascending | Category Room Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
65 | Room065 | User searching room based on Rating Descending | Category Room Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
66 | Room066 | User searching room based on Price Highest Price | Category Room Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
67 | Room067 | User searching room based on Price Lowest Price | Category Room Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
68 | Room068 | User searching room based on Guest Rating | Category Room Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
69 | Room069 | User searching room based on Amenities | Category Room Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
70 | Room070 | User searching Room in Category Room page | Order Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
71 | Room071 | User see Order Detail Page | Order Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
72 | Room072 | User confirm the order use Bank Wire as Payment Method | Order Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
73 | Room073 | User confirm the order use check as Payment Method | Order Detail Page | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
74 | Room074 | User Checkout Room from cart Item | Cart | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
75 | Room075 | User delete Cart Item | Cart | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
76 | Room076 | User confirm the order use Pay Pal as Payment Method | Order Confirmation | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
77 | Room077 | User see Order Confirmation | Order Confirmation | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
78 | Room078 | User see Order history and details | Order History | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
79 | Room079 | User Checkout order Room Hotel as a Guest | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
80 | Room080 | User register Guest Information but Firstname is empty | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
81 | Room081 | User register Guest Information but Lastname is empty | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
82 | Room082 | User register Guest Information but Email is empty | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
83 | Room083 | User register Guest Information but Password is empty | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
84 | Room084 | User register Guest Information but Mobile is empty | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
85 | Room085 | User register Guest Information but Email is Registered | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
86 | Room086 | User register Guest Information but Password less than 5 characters | Order as a Guest | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
87 | Room087 | User sending message via Contact Us | Contact Us | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty
88 | Room088 | User Logout Aplikasi Booking Room Hotel | Logout | WebBookingRoom | Positive | 15-09-2021 |  |  | Arisa Hazriaty

## Scenario Cases
Test Case ID | Feature | Precondition | Positive/Negative | Scenario Name | Test Case Objective | Test Step | Expected Behaviour | Actual Behaviour | Result | Automated | Bug-ID
Room001 | Register Account | User open the Login Authentication Page | Positive | User create Account Aplikasi Booking Room Hotel | User able to create Account Booking Room Hotel | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Click Create an Account 3. Set Firstname 4. Set Lastname 5. Set Password 6. Click Register Button | User able to create Account Booking Room Hotel | User able to create Account Booking Room Hotel | Passed | Yes
Room002 | Register Account | User open the Login Authentication Page | Negative | User Create Account with Email Registered | User should enter new email | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Click Create an Account 6. Click Register Button | User should enter new email | User should enter new email | Passed | Yes
Room003 | Register Account | User open the Login Authentication Page | Negative | User Register Account but FirstName is Numeric | User should input First name is Character | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Set Firstname isNumeric 4. Set Lastname 5. Set Password 6. Click Register Button | User should input First name is Character | User should input First name is Character | Passed | No
Room004 | Register Account | User open the Login Authentication Page | Negative | User Register Account but LastName is Numeric | User should input Last name is Character | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Set Firstname 4. Set Lastname isNumeric 5. Set Password 6. Click Register Button | User should input Last name is Character | User should input Last name is Character | Passed | No
Room005 | Register Account | User open the Login Authentication Page | Negative | User Register Account but FirstName is Special Character | User should input First name is Character | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Set Firstname is Special Character 4. Set Lastname 5. Set Password 6. Click Register Button | User should input First name is Character | User should input First name is Character | Passed | No
Room006 | Register Account | User open the Login Authentication Page | Negative | User Register Account but LastName is Special Character | User should input Last name is Character | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Set Firstname 4. Set Lastname is Special Character 5. Set Password 6. Click Register Button | User should input Last name is Character | User should input Last name is Character | Passed | No
Room007 | Register Account | User open the Login Authentication Page | Negative | User Register Account but Password is less than 5 Chars | User should input Password minimal 5 Chars | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Set Firstname 4. Set Lastname 5. Set Password minimal 5 Chars 6. Click Register Button | User should input Password minimal 5 Chars | User should input Password minimal 5 Chars | Passed | No
Room008 | Register Account | User open the Login Authentication Page | Positive | User Register Account but FirstName only 1 Character | User able to Register account with FirstName 1 Character | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Set Firstname is 1 Character 4. Set Lastname 5. Set Password 6. Click Register Button | User able to Register account with FirstName 1 Character | User able to Register account with FirstName 1 Character | Passed | No
Room009 | Register Account | User open the Login Authentication Page | Positive | User Register Account but LarstName only 1 Character | User able to Register account with LastName 1 Character | 1. User open the Aplikasi Booking Room Hotel 2. Enter Email Address 3. Set Firstname 4. Set Lastname is One Character 5. Set Password 6. Click Register Button | User able to Register account with LastName 1 Character | User able to Register account with LastName 1 Character | Passed | No
Room010 | Register Account | User open the Login Authentication Page | Negative | User Create Account with Email Registered | User should register valid email address | 1. User open the Aplikasi Booking Room Hotel 2. Set Email Address Empty 3. Click Create an Account | User should register valid email address | User should register valid email address | Passed | Yes
Room011 | Login | User open the Login Authentication Page | Positive | User login Aplikasi Booking Room Hotel | User able to login Aplikasi Booking Room Hotel | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in | User able to login Aplikasi Booking Room Hotel | User able to login Aplikasi Booking Room Hotel | Passed | Yes
Room012 | Login | User open the Login Authentication Page | Negative | User login Aplikasi Booking Room Hotel but invalid email format | User should input valid email address | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input invalid Email Address 4. Input Password 5. Click Sign in | User should input valid email address | User should input valid email address | Passed | Yes
Room013 | Forgot Password | User open the Login Authentication Page | Positive | User forgot the password | User able to get new Password after forgot password | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Click Forgot Password Link 4. Input Valid Email Address 5. Click Retrieve Password | User able to get new Password after forgot password | An error occured while sending email | Failed | No | Bug-001
Room014 | Address | User open the Address Page | Positive | User Add a New the Address | User able to Add new the Address | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Add a new Addresses 8. Fill All Mandatory Fields 9. Click Save Button | User able to Add new the Address | User able to Add new the Address | Passed | No
Room015 | Address | User open the Address Page | Negative | User Add a New the Address but address1 is empty | Address 1 is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Add a new Addresses 8. Fill All Mandatory Fields 9. Set Address1 empty 9. Click Save Button | Address 1 is required | Address 1 is required | Passed | No
Room016 | Address | User open the Address Page | Negative | User Add a New the Address but city is empty | City is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Add a new Addresses 8. Fill All Mandatory Fields 9. Set city empty 9. Click Save Button | City is required | City is required | Passed | No
Room017 | Address | User open the Address Page | Negative | User Add a New the Address but phone is empty | Phone is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Add a new Addresses 8. Fill All Mandatory Fields 9. Set phone empty 9. Click Save Button | Phone is required | Phone is required | Passed | No
Room018 | Address | User open the Address Page | Negative | User Add a New the Address but country is empty | Country is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Add a new Addresses 8. Fill All Mandatory Fields 9. Set country empty 9. Click Save Button | Country is required | Country is required | Passed | No
Room019 | Address | User open the Address Page | Negative | User Add a New the Address but the Zip/Postal is empty | Zip/postal code is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Add a new Addresses 8. Fill All Mandatory Fields 9. Set zip/postal code empty 9. Click Save Button | Zip/postal code is required | Zip/postal code is required | Passed | No
Room020 | Address | User open the Modify Address Page | Positive | User Update the Address | User able to update the Address | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Update the Required field 9. Click Save Button | User able to update the Address | User able to update the Address | Passed | No
Room021 | Address | User open the Modify Address Page | Negative | User update the Address but firstname is Empty | firstname is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Set firstname is empty 9. Click Save Button | firstname is required | firstname is required | Passed | No
Room022 | Address | User open the Modify Address Page | Negative | User update the Address but lastname is Empty | lastname is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Set lastname is empty 9. Click Save Button | lastname is required | lastname is required | Passed | No
Room023 | Address | User open the Modify Address Page | Negative | User update the Address but address1 is Empty | Address 1 is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Set Address1 is empty 9. Click Save Button | Address 1 is required | Address 1 is required | Passed | No
Room024 | Address | User open the Modify Address Page | Negative | User update the Address but city is Empty | City is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Set city is empty 9. Click Save Button | City is required | City is required | Passed | No
Room025 | Address | User open the Modify Address Page | Negative | User update the Address but phone number is Empty | Phone number is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Set phone number is empty 9. Click Save Button | Phone number is required | Phone number is required | Passed | No
Room026 | Address | User open the Modify Address Page | Negative | User update the Address but the zip/postal code is Empty | Zip/postal code is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Set zip/postal code is empty 9. Click Save Button | Zip/postal code is required | Zip/postal code is required | Passed | No
Room027 | Address | User open the Modify Address Page | Negative | User update the Address but the Adress title is Empty | Address title is required | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click Update the Address 8. Set Address title is empty 9. Click Save Button | Address title is required | Address title is required | Passed | No
Room028 | Address | User open the Personal Information | Positive | User Delete the Address | User able to delete the Address | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Click delete one of the Address 9. Click ok Confirmation pop up 10. Check the Alamat deleted | User able to delete the Address | User able to delete the Address | Passed | No
Room029 | Address | User open the Personal Information | Positive | User see the Address | User able to see the Address | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Adresses 7. Check the list Address | User able to see the Address | User able to see the Address | Passed | No
Room030 | Personal Information | User open the Homepage | Positive | User see Personal Information | User able to see My Personal Information | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click My Personal Information 7. Check the Your Personal Information | User able to see My Personal Information | User able to see My Personal Information | Passed | No
Room031 | Order History | User open the Homepage | Positive | User see Order history and details | User able to see Order history and details | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Order history and details 7. Check the Order History | User able to see Order history and details | User able to see Order history and details | Passed | No
Room032 | Credit Slips | User open the Homepage | Positive | User see My Credit Slips | User able to see My Credit Slips | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Credit Slips 7. Check the Credit Slips | User able to see My Credit Slips | User able to see My Credit Slips | Passed | No
Room033 | Search Room | User open the Homepage | Negative | User searching Hotel but date Check In less than today | User not able to searching Hotel but date Check In less than today | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Fill All Mandatory fields 8. Set date Check In less than today 9. Click Search Now | User not able to searching Hotel but date Check In less than today | User not able to searching Hotel but date Check In less than today | Passed | No
Room034 | Search Room | User open the Homepage | Negative | User searching Hotel but Hotel Location Empty | User not able to searching Hotel but Hotel Location Empty | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Fill All Mandatory fields 8. Set Hotel location empty 9. Click Search Now | User not able to searching Hotel but Hotel Location Empty | User not able to searching Hotel but Hotel Location Empty | Passed | No
Room035 | Search Room | User open the Homepage | Negative | User searching Hotel but room not selected | User not able to searching Hotel but room not selected | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Fill All Mandatory fields 8. Set Select Hotel default 9. Click Search Now | User not able to searching Hotel but room not selected | User not able to searching Hotel but room not selected | Passed | No
Room036 | Search Room | User open the Homepage | Negative | User searching Hotel but not fields selected | User not able to searching Hotel but not fields selected | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Click Search Now | User not able to searching Hotel but not fields selected | User not able to searching Hotel but not fields selected | Passed | No
Room037 | Search Room | User open the Homepage | Negative | User searching Hotel but only set Hotel Location | User not able to searching Hotel only set room Location | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Set Hotel location 9. Click Search Now | User not able to searching Hotel only set room Location | User not able to searching Hotel only set room Location | Passed | No
Room038 | Search Room | User open the Homepage | Negative | User searching Hotel but only set the Hotel | User not able to searching Hotel only set the Hotel | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Select the Hotel 9. Click Search Now | User not able to searching Hotel only set the Hotel | User not able to searching Hotel only set the Hotel | Passed | No
Room039 | Search Room | User open the Homepage | Negative | User searching Hotel but only set Check In Date | User not able to searching Hotel but only set Check In Date | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Set date Check In 9. Click Search Now | User not able to searching Hotel but only set Check In Date | User not able to searching Hotel but only set Check In Date | Passed | No
Room040 | Search Room | User open the Homepage | Negative | User searching Hotel but only set Check Out Date | User not able searching Hotel but only set Check Out Date | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Set date Check Out 9. Click Search Now | User not able searching Hotel but only set Check Out Date | User not able searching Hotel but only set Check Out Date | Passed | No
Room041 | Search Room | User open the Homepage | Negative | User searching Hotel but date Check In and Check Out is today | User not able searching Hotel but date Check In and Check Out is today | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Set date Check In - Check Out today 9. Click Search Now | User not able searching Hotel but date Check In and Check Out is today | User not able searching Hotel but date Check In and Check Out is today | Passed | No
Room042 | Homepage | User open the Homepage | Positive | User validate cart | User able validate cart | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Input Hotel Location 8. Select The Hotel 9. Set the Check in and Checkout Button 10. Click Book Now 11. Click Cart in Header 12. Check the cart | User able validate cart | User able validate cart | Passed | No
Room043 | Homepage | User open the Homepage | Positive | User see Profile Account | User able to see Profile Account | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Click Icon Profile 8. Select Account | User able to see Profile Account | User able to see Profile Account | Passed | No
Room044 | Homepage | User open the Homepage | Positive | User see Burger Menu | User able see Burger Menu | 1. User open the Aplikasi Booking Room Hotel 2. User Click Burger Menu | User able see Burger Menu | User able see Burger Menu | Passed | No
Room045 | Homepage | User open the Homepage | Positive | User see Interior section | User able see Interior section | 1. User open the Aplikasi Booking Room Hotel 2. Scroll down until view Interior Section | User able see Interior section | User able see Interior section | Passed | No
Room046 | Homepage | User open the Homepage | Positive | User see Amenities section | User able see Amenities section | 2. User open the Aplikasi Booking Room Hotel 2. Scroll down until view Amenities Section | User able see Amenities section | User able see Amenities section | Passed | No
Room047 | Booking Now | User open the Homepage | Positive | User see Our Room section | User able see Our Room section | 1. User open the Aplikasi Booking Room Hotel 2. Scroll down until view Interior Section | User able see Our Room section | User able see Our Room section | Passed | No
Room048 | Booking Now | User open the Homepage | Positive | User Booking Deluxe Rooms in Our Room section | User able to Booking Deluxe Rooms in Our Room section | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now | Room successfully added to your cart | Room successfully added to your cart | Passed | No
Room049 | Booking Now | User open the Homepage | Positive | User Booking Executive Rooms in Our Room section | User able to Booking Executive Rooms in Our Room section | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Executive Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now | User able to Booking Executive Rooms in Our Room section | User able to Booking Executive Rooms in Our Room section | Passed | No
Room050 | Booking Now | User open the Homepage | Positive | User Booking General Rooms in Our Room section | User able Booking General Rooms in Our Room section | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at General Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now | User able Booking General Rooms in Our Room section | User able Booking General Rooms in Our Room section | Passed | No
Room051 | Room Detail Page | User open the Homepage | Positive | User Booking Luxury Rooms in Our Room section | User able Booking Luxury Rooms in Our Room section | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Luxury Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now | User able Booking Luxury Rooms in Our Room section | User able Booking Luxury Rooms in Our Room section | Passed | No
Room052 | Room Detail Page | User open the Room Detail Page | Positive | User modify search in Detail Room Page | User able modify search in Detail Room Page | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now one of the rooms 3. set Date CheckIn & Date Checkout 4. Set the Searched Result 6. Click Search Room | User able modify search in Detail Room Page | User able modify search in Detail Room Page | Passed | No
Room053 | Room Detail Page | User open the Room Detail Page | Positive | User view photos in Detail Room Page | User able view photos in Detail Room Page | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now one of the rooms 3. Select the photos Description | User able view photos in Detail Room Page | User able view photos in Detail Room Page | Passed | No
Room054 | Room Detail Page | User open the Room Detail Page | Positive | User write a review in Detail Room Page | User able write a review in Detail Room Page | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now one of the rooms 3. Write a review Room | User able write a review in Detail Room Page | User able write a review in Detail Room Page | Passed | No
Room055 | Room Detail Page | User open the Room Detail Page | Positive | User see Room Information in Detail Room Page | User able see Room Information in Detail Room Page | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now one of the rooms 3. Click Tab Room Information | User able see Room Information in Detail Room Page | User able see Room Information in Detail Room Page | Passed | No
Room056 | Room Detail Page | User open the Room Detail Page | Positive | User see Refund Policies in Detail Room Page | User able see Refund Policies in Detail Room Page | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now one of the rooms 3. Click Tab Refund Polices | User able see Refund Policies in Detail Room Page | User able see Refund Policies in Detail Room Page | Passed | No
Room057 | Room Detail Page | User open the Room Detail Page | Positive | User see Reviews in Detail Room Page | User able see Reviews in Detail Room Page | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now one of the rooms 3. Click Tab Room Reviews | User able see Reviews in Detail Room Page | User able see Reviews in Detail Room Page | Passed | No
Room058 | Footer | User open the Homepage | Positive | User see Testimony Guest in testimoni section | User able see Testimony Guest in testimoni section | 1. User open the Aplikasi Booking Room Hotel 2. Scroll to Testimony Guest 3. Check testimony Guest | User able see Testimony Guest in testimoni section | User able see Testimony Guest in testimoni section | Passed | No
Room059 | Footer | User open the Homepage | Positive | User change language in footer section | User able change language in footer section | 1. User open the Aplikasi Booking Room Hotel 2. Scrol to Language Footer 3. Set the Language | User able change language in footer section | User able change language in footer section | Passed | No
Room060 | Footer | User open the Homepage | Positive | User see about information in footer section | User able see about information in footer section | 1. User open the Aplikasi Booking Room Hotel 2. Scrol to About Footer 3. Check the About | User able see about information in footer section | User able see about information in footer section | Passed | No
Room061 | Footer | User open the Homepage | Positive | User Subscribe to Get Notifications in footer section | User able Subscribe to Get Notifications in footer section | 1. User open the Aplikasi Booking Room Hotel 2. Scrol to Language Footer 3. Enter the email 4. Click Subscribe | User able Subscribe to Get Notifications in footer section | User able Subscribe to Get Notifications in footer section | Passed | No
Room062 | Footer | User open the Homepage | Positive | User follows Social Media in footer section | User able follows Social Media in footer section | 1. User open the Aplikasi Booking Room Hotel 2. Scrol to Language Footer 3. Select One Of Social Media 4. Check Social Media display on new tab | User able follows Social Media in footer section | User able follows Social Media in footer section | Passed | No
Room063 | Footer | User open the Homepage | Positive | User see Explore Information in footer section | User able see Explore Information in footer section | 1. User open the Aplikasi Booking Room Hotel 2. Scrol to Explore Footer 3. Select One Of Content the Explore 4. Check Content Display | User able see Explore Information in footer section | User able see Explore Information in footer section | Passed | No
Room064 | Category Room Page | User open the Category Room | Positive | User searching room based on Rating Ascending | User able to Searching room based on Rating Ascending | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Sort by Rating Ascending | User able to Searching room based on Rating Ascending | User able to Searching room based on Rating Ascending | Passed | No
Room065 | Category Room Page | User open the Category Room | Positive | User searching room based on Rating Descending | User able to Searching room based on Rating Descending | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Sort by Rating Descending | User able to Searching room based on Rating Descending | User able to Searching room based on Rating Descending | Passed | No
Room066 | Category Room Page | User open the Category Room | Positive | User searching room based on Price Highest Price | User able to searching room based on Price Highest Price | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Sort by Rating Highest Price | User able to searching room based on Price Highest Price | User able to searching room based on Price Highest Price | Passed | No
Room067 | Category Room Page | User open the Category Room | Positive | User searching room based on Price Lowest Price | User able to searching room based on Price Lowest Price | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Sort by Rating Lowest Price | User able to searching room based on Price Lowest Price | User able to searching room based on Price Lowest Price | Passed | No
Room068 | Category Room Page | User open the Homepage | Positive | User searching room based on Guest Rating | User able to searching room based on Guest Rating | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Select Guest Rating | User able to searching room based on Guest Rating | User able to searching room based on Guest Rating | Passed | No
Room069 | Category Room Page | User open the Homepage | Positive | User searching room based on Amenities | User able to searching room based on Amenities | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Select the Amenities | User able to searching room based on Amenities | User able to searching room based on Amenities | Passed | No
Room070 | Order Detail Page | User Checkout the room page | Positive | User searching Room in Category Room page | User able to searching Room in Category Room page | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Set Search Rooms 8. Click Search Rooms | User able to searching Room in Category Room page | User able to searching Room in Category Room page | Passed | No
Room071 | Order Detail Page | User Checkout the room page | Positive | User see Order Detail Page | User able to see Order Detail Page | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Click Search Now 8. Set Quantity 9. Click Book Now 10. Click Proceed Check Out | User able to see Order Detail Page | User able to see Order Detail Page | Passed | No
Room072 | Order Detail Page | User Checkout the room page | Positive | User confirm the order use Bank Wire as Payment Method | User able to confirm the order use Bank Wire as Payment Method | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Click Search Now 8. Set Quantity 9. Click Book Now 10. Click Proceed Check Out | User able to confirm the order use Bank Wire as Payment Method | User able to confirm the order use Bank Wire as Payment Method | Passed | Yes
Room073 | Order Detail Page | User Checkout the room page | Positive | User confirm the order use check as Payment Method | User able to confirm the order use check as Payment Method | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Click Search Now 8. Set Quantity 9. Click Book Now 10. Click Proceed Check Out 11. Set Guest Information 12. Click Proceed 13. Click Agree 14. Select Pay by Bank Wire | User able to confirm the order use check as Payment Method | User able to confirm the order use check as Payment Method | Passed | Yes
Room074 | Cart | User add Quatity to cart | Positive | User Checkout Room from cart Item | User able Checkout Room from cart Item | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Input Hotel Location 8. Select The Hotel 9. Set the Check in and Checkout Button 10. Click Book Now 11. Click Cart in Header 12. Check the cart 13. Click Checkout 14. Click Proceed 15. Click Agree 16. Select Payment by Bank Wire 17. Click I confirm my order | User able Checkout Room from cart Item | User able Checkout Room from cart Item | Passed | No
Room075 | Cart | User add Quatity to cart | Positive | User delete Cart Item | User able to delete Cart Item | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Home 7. Input Hotel Location 8. Select The Hotel 9. Set the Check in and Checkout Button 10. Click Book Now 11. Click Cart in Header 12. Click Delete Cart | User able to delete Cart Item | User able to delete Cart Item | Passed | No
Room076 | Order Confirmation | User see Summary Room & Price | Positive | User confirm the order use Pay Pal as Payment Method | User able to confirm the order use Pay Pal as Payment Method | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Click Search Now 8. Set Quantity 9. Click Book Now 10. Click Proceed Check Out 11. Set Guest Information 12. Click Proceed 13. Click Agree 14. Select Pay by Pay Pal 15. Click I want to Confirm my order | User able to confirm the order use Pay Pal as Payment Method | User able to confirm the order use Pay Pal as Payment Method | Passed | No
Room077 | Order Confirmation | User see Summary Room & Price | Positive | User see Order Confirmation | User able to see Order Confirmation | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Click Search Now 8. Set Quantity 9. Click Book Now 10. Click Proceed Check Out 11. Set Guest Information 12. Click Proceed 13. Click Agree 14. Select Pay by Pay Pal 15. Click I want to Confirm my order 16. Check Order Confirmation | User able to see Order Confirmation | User able to see Order Confirmation | Passed | No
Room078 | Order History | User logged in Aplikasi Booking Room Hotel | Positive | User see Order history and details | User able to see Order history and details | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Order History and details 7. Check Order History | User able to see Order history and details | User able to see Order history and details | Passed | No
Room079 | Order as a Guest | User open Rooms & Price Summary Page | Positive | User Checkout order Room Hotel as a Guest | User should Register Guest Information | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Click Save. | User able to Checkout order Room Hotel as a Guest | User able to Checkout order Room Hotel as a Guest | Passed | No
Room080 | Order as a Guest | User open Rooms & Price Summary Page | Negative | User register Guest Information but Firstname is empty | Firstname is required in Guest Information | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Set Firstname empty 9. Click Save. | Firstname is required in Guest Information | Firstname is required in Guest Information | Passed | No
Room081 | Order as a Guest | User open Rooms & Price Summary Page | Negative | User register Guest Information but Lastname is empty | Lastname is required in Guest Information | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Set Lastname empty 9. Click Save. | Lastname is required in Guest Information | Lastname is required in Guest Information | Passed | No
Room082 | Order as a Guest | User open Rooms & Price Summary Page | Negative | User register Guest Information but Email is empty | Email is required in Guest Information | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Set Email empty 9. Click Save. | Email is required in Guest Information | Email is required in Guest Information | Passed | No
Room083 | Order as a Guest | User open Rooms & Price Summary Page | Negative | User register Guest Information but Password is empty | Password is required in Guest Information | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Set Password empty 9. Click Save. | Password is required in Guest Information | Password is required in Guest Information | Passed | No
Room084 | Order as a Guest | User open Rooms & Price Summary Page | Negative | User register Guest Information but Mobile is empty | Mobile is required in Guest Information | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Set Mobile empty 9. Click Save. | Mobile is required in Guest Information | Mobile is required in Guest Information | Passed | No
Room085 | Order as a Guest | User open Rooms & Price Summary Page | Negative | User register Guest Information but Email is Registered | Email is required in Guest Information | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Set Email registered 9. Click Save. | Email is required in Guest Information | Email is required in Guest Information | Passed | No
Room086 | Order as a Guest | User open Rooms & Price Summary Page | Negative | User register Guest Information but Password less than 5 characters | Password is minimal 5 Characters | 1. User open the Aplikasi Booking Room Hotel 2. Click Book Now at Deluxe Room 3. set Date CheckIn & Date Checkout 4. Set Quantity Rooms 5. Check Stok Room 6. Click Book Now 7. Click Proceed 8. Input all Mandatory fields 9. Set Password < 5 Chars 9. Click Save. | Password is minimal 5 Characters | Password is minimal 5 Characters | Passed | No
Room087 | Contact Us | User open the Homepage | Positive | User sending message via Contact Us | User able to sending message via Contact Us | 1. User open the Aplikasi Booking Room Hotel 2. Click Burger Menu 3. Select Contact Us 4. Select Subject 5. Put the Message.Query 6. Attach File 7. Click Send Message | User able to sending message via Contact Us | User able to sending message via Contact Us | Passed | No
Room088 | Logout | User logged in Aplikasi Booking Room Hotel | Positive | User Logout Aplikasi Booking Room Hotel | User able to Logout Aplikasi Booking Room Hotel | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Click Logout Button | User able to Logout Aplikasi Booking Room Hotel | User able to Logout Aplikasi Booking Room Hotel | Passed | No
[9 empty] | Total Scenario | 88
[9 empty] | Total Scenario Passed | 87
[9 empty] | Total Scenario Failed | 1
[9 empty] | Total Scenario Automated | 7
[9 empty] | Total Scenario Running Manual | 81
[9 empty] | Total Scenario Positive | 52
[9 empty] | Total Scenario Negative | 36

## UAT Report (hidden)
Two Wheelers EFP
- Project Information - |  | - Test Result - |  |  |  | - Execution Plan - |  | - Actual Execution -
Report Date. | 2021-09-15 | Status. | OK |  |  | Start Date. | 0 | Start Date. | 0
Project No. | UAT | Completion. | 0% Tested Correctly / 0% Executed |  |  | Finish Date. | 0 | Finish Date. | 0
Test Env. | C1 | Total Test Case. | 74
- Total Results To Date -
Status. | Planned #. | Planned % | Actual #. | Actual % from Result to Date.
Plan. | 83 | 100% | 0 | 0%
Tested correctly | 83 | 100% | 0 | 0%
Tested with non Stopping Defect |  |  | 0 | 0%
Tested with Showstopper |  |  | 0 | 0%
In Progress |  |  | 0 | 0%
N/A |  |  | 0 | 0%
Not Tested |  |  | 0 | 0%
- Defect / Issue Details -
Defect ID (#) | Defect Name | Description |  | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case
Bug001 | Error When User sending Email Forgot Password | High |  | User able to get new Password after forgot password | Open | 0 | 0 | 0 | 0
Bug002 | Write a review not clickable | Normal |  | User able to review Room Hotel | Open | 0 | 0 | 0 | 0
Bug003 | Sorting not Sortable | Normal |  | User able to Searching room based on Rating Ascending or Vice Versa | Open | 0 | 0 | 0 | 0
0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
No. | Type. | Scenario ID | Scenario Case |  |  |  |  | Result.
1 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
2 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
3 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
4 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
5 | Positive | User Add a New the Address but country is empty | #VALUE! |  |  |  |  | 0
6 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
7 | #VALUE! | User Add a New the Address but the Zip/Postal is empty | #VALUE! |  |  |  |  | #VALUE!
8 | Positive | #VALUE! | User update the Address but phone number is Empty |  |  |  |  | 0
9 | #REF! | User Update the Address | #VALUE! |  |  |  |  | #REF!
10 | #REF! | User update the Address but firstname is Empty | #VALUE! |  |  |  |  | #REF!
11 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
12 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
13 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
14 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!

## SIT Scenario (hidden)
No | Scenario ID | Scenario Cases | Product Code | Involved System or Application | Pre Condition | Scenario Type | Planned Date | Execution Date | Status | Tester | Notes

## Reff Table (hidden)
Test Cycle | Test Env | Progress / Result | Test Priority | Scenario Type | Status | Defect / Issue | Defect Status
SIT | C1 | OK | High | Positive | Tested correctly | DEFECT | Open
| PreProd | OK | High | Positive | Tested correctly | DEFECT | Open
UAT | C2 | NOT OK | Medium | Negative | Tested with non Stopping Defect | ISSUE | In Progress
| C3 | In Progress | Low | Regression | Not Tested |  | Closed
| PreProd |  | Critical |  | N/A
| Production |  |  |  | In Progress
Tested with Showstopper

## Findings
Jira ID (#) | Title | Priority | Step to Reproduce | Expected Result | Actual Result | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case | Remarks
Bug001 | Error When User sending Email Forgot Password | High | 1. Click SignIn 2. Click link Forgot Password 3. Set Valid Email Address 4. Click Retrieve Password | User able to get new Password after forgot password | An error occurred while sending the email. |  | Open
Bug002 | Write a review not clickable | Normal | 1. Click Booking Now from Homepage 2. Click Write a review in Room Detail Page | User able to review Room Hotel | Write a review not clickable |  | Open
Bug003 | Sorting not Sortable | Normal | 1. User open the Aplikasi Booking Room Hotel 2. click Sign In link 3. Input valid Email Address 4. Input valid Password 5. Click Sign in 6. Search Hotel 7. Sort by Rating Ascending | User able to Searching room based on Rating Ascending or Vice Versa | User able to Searching room based on Rating Ascending or Vice Versa |  | Open